## Executive Summary
RHM SPRING 2025 MARKETING PROPOSAL
Resort and Hospitality Management Program ¦ College of Business and Economics
CAMPAIGN OVERVIEW
Proposal Date: | January 2025 | Campaign Duration: | January - May 2025
Prepared By: | Ben Howerton, GA | Primary Goal: | Recruit current BSU students to RHM
Total Budget: | 2090 | Expected Reach: | 120,000 - 237,000 impressions*
Campaign Destination: | Certificate Programs Landing Page
BUDGET SUMMARY BY CHANNEL
Channel Category | Cost | % of Budget | Est. Impressions* | CPM
Paid Student Media | 1250 | 59.81% | 75000 | 16.6667
Paid Social (Meta/IG) | 560 | 26.79% | 105000 | 5.3333
Paid Print (Shuttle Stops) | 280 | 13.4% | 12000 | 23.3333
Free Channels (COBE Internal) | 0 | 0 | 45000 | -
TOTAL | 2090 | 100% | 237000 | 8.8186
*ESTIMATE - Impression numbers are approximations. Yellow-highlighted cells need validation with actual analytics data.
KEY CAMPAIGN MILESTONES
Month | Key Activities
February | Arbiter Print Ad (Feb 20) ¦ Shuttle Stop Posters Deploy ¦ MBEB Screens Launch
March | Arbiter Web Banner Live ¦ Tabling Events Begin ¦ Student Events Newsletter Feature
April | Blueprint Magazine Publication (Apr 24) ¦ Peak Instagram Campaign ¦ Newsletter Feature #2
May | End of Semester Push ¦ Final Analytics Review ¦ Semester Report

## Channel Detail
SPRING 2025 CHANNEL MARKETING PLAN
Channel | Type | Rate | Unit | Jan | Feb | Mar | Apr | May | Spring Total | Notes/Delivery Details
PAID CHANNELS
Blueprint Summer Magazine | Print | 450 | per/Period | 0 | 0 | 0 | 450 | 0 | 450 | Half-page ad (4.75x11 or 8.5x5.5). Published Apr 24. 3,000 copies distributed at graduation, summer orientation, Fall move-in.
Arbiter Web Banner | Digital | 400 | per/Month | 0 | 0 | 400 | 0 | 0 | 400 | 728x90px Banner. ~20,000 monthly site views. Run in March for peak enrollment season.
Arbiter Print Ad | Print | 400 | per/Issue | 0 | 400 | 0 | 0 | 0 | 400 | 1/2 page print ad. Feb 20 issue. 2,000 copies distributed on campus + downtown Boise. RHM 10% discount available.
Shuttle Stop Posters | Print | 14 | per/Poster | 0 | 0 | 280 | 0 | 0 | 280 | 20 posters at $14 each. Target Blue/Orange bus crossover points. Cold weather = high bus ridership.
Social Media (Meta/IG) | Digital | 140 | per/Month | 0 | 140 | 140 | 140 | 140 | 560 | $5/day targeting Boise residents + BSU students. Run in April before semester ends.
COBE INTERNAL CHANNELS (FREE) - All requests to cobe-info@boisestate.edu
@boisestatecobe Instagram | Social | 0 | per/Post | 3-4/wk | 3-4/wk | 3-4/wk | 3-4/wk | 3-4/wk | Free | Reels outperform static. 10 business day lead time. Submit to cobe-info with graphics (1080x1080 or 1080x1920).
@boisestatecobe LinkedIn | Social | 0 | per/Post | 2-3/wk | 2-3/wk | 2-3/wk | 2-3/wk | 2-3/wk | Free | Professional/employer focus. Tag industry partners. 1920x1080 banners.
Student Events Newsletter | Email | 0 | per/Feature | - | ✓ | ✓ | ✓ | - | Free | Feature every few months (avoid tune-out). Vary messaging each time. 10-15 day lead time.
Bronco Business News | Email | 0 | per/Feature | - | - | ✓ | - | ✓ | Free | Broader COBE audience. Coordinate with Kate for timing.
MBEB Digital Screens | Digital | 0 | per/Screen | ✓ | ✓ | ✓ | ✓ | ✓ | Free | 1920x1080px. Dark background, white text. NO logo overlays (Clean Screen Rule).
SUB/Library Screens | Digital | 0 | per/Screen | ✓ | ✓ | ✓ | ✓ | ✓ | Free | Campus-wide digital screen network. High traffic locations.
Capital BLVD Tabling | Event | 0 | per/Event | - | - | ✓ | ✓ | - | Free | Weekly tabling on Capitol BLVD + Brady garage sidewalk. High COBE student traffic.
Class Visits | Event | 0 | per/Visit | ✓ | ✓ | ✓ | - | - | Free | Present in intro-level business courses. QR-coded handouts drive to landing page.
Localist Calendar | Digital | 0 | per/Event | ✓ | ✓ | ✓ | ✓ | ✓ | Free | Add events to Boise State Localist. Shows on COBE + university-wide event calendars.
TOTAL SPRING BUDGET |  |  |  | 0 | 540 | 820 | 590 | 140 | 2090
REQUEST PROCESS
Email: cobe-info@boisestate.edu ¦ Subject: PROGRAM REQUEST - [Channel] - [Date Range]
Include: Channel(s), target date, copy draft (≤100 words), CTA link, assets with alt text (1080x1080, 1080x1920, or 1920x1080)

## Monthly Calendar
SPRING 2025 MARKETING CALENDAR
Activity | January | February | March | April | May | Field to Fork Feb 12th
PAID CHANNELS
Blueprint Magazine |  |  |  | Publication (Apr 24) | Active
Arbiter Web Banner |  |  | Banner Live
Arbiter Print |  | Feb 20 Issue
Shuttle Stop Posters |  |  | Deploy Posters
Instagram/Meta Ads |  | $5/day Campaign | Active | Active
COBE CHANNELS (@boisestatecobe)
Instagram Posts/Reels | 3-4/week | 3-4/week | 3-4/week | 3-4/week | 3-4/week
LinkedIn Posts | 2-3/week | 2-3/week | 2-3/week | 2-3/week | 2-3/week
Student Events Newsletter |  | Feature #1 | Feature #2 | Feature #3
Bronco Business News |  |  | Feature |  | Feature
MBEB Screens | Active | Active | Active | Active | Active
SUB/Library Screens | Active | Active | Active | Active | Active
Tabling Events |  |  | Weekly | Weekly
Class Visits | Intro Classes | Intro Classes | Intro Classes
Localist Calendar | Add Events | Add Events | Add Events | Add Events | Add Events
LEAD TIME REMINDERS
Channel | Lead Time | Notes
Instagram/LinkedIn | 10 business days | Urgent posts require marketing manager approval
Email Newsletter | 10-15 business days | Complex newsletters need more time
Web Updates | 10 business days | Include exact copy, URL, alt text
Events/Fairs | 3-6 weeks | Longer for venue and partner coordination

## ROAS & Impressions
EXPECTED RETURN ON AD SPEND (ROAS) ANALYSIS
Since our primary KPI is awareness/impressions (not direct conversions), we measure ROAS as Cost Per Thousand Impressions (CPM).
Channel | Cost | Est. Impressions* | CPM | Reach Quality | Targeting Accuracy | ROAS Rating | Data Source
Blueprint Magazine | 450 | 9000 | 50 | High - Print to hand | Medium - General BSU | ★★★☆☆ | Student Media rate card
Arbiter Web Banner | 400 | 20000 | 20 | Medium - Banner ads | Medium - BSU readers | ★★★★☆ | Arbiter: 20K monthly views
Arbiter Print | 400 | 6000 | 66.6667 | High - Print to hand | Medium - General BSU | ★★★☆☆ | 2K copies x 3 readers/copy
Shuttle Stop Posters | 280 | 12000 | 23.3333 | High - Captive audience | High - Bus riders | ★★★★★ | ESTIMATE - needs validation
Meta/Instagram Ads | 140 | 35000 | 4 | Medium - Digital | High - Targeted demo | ★★★★★ | Meta Ads Manager projections
@boisestatecobe IG | 0 | 12000 | - | Medium - Organic reach | High - COBE followers | ★★★★★ | ESTIMATE - need follower count
@boisestatecobe LI | 0 | 5000 | - | Medium - Professional | High - COBE network | ★★★★☆ | ESTIMATE - need follower count
Student Events Newsletter | 0 | 4000 | - | High - Email open rate | Very High - Subscribers | ★★★★★ | ESTIMATE - need list size/open rate
Bronco Business News | 0 | 3000 | - | High - Email open rate | High - COBE community | ★★★★★ | ESTIMATE - need list size/open rate
MBEB/Campus Screens | 0 | 20000 | - | Medium - Passive view | High - COBE students | ★★★★☆ | ESTIMATE - based on foot traffic
Tabling Events | 0 | 1000 | - | Very High - In-person | Very High - Direct | ★★★★★ | ~50 contacts x 4 events x 5 touches
Localist Calendar | 0 | 500 | - | Medium - Discovery | Medium - Event seekers | ★★★☆☆ | ESTIMATE - university calendar reach
KEY INSIGHTS
• Best CPM: Instagram/Meta ads deliver ~$4 CPM with precise demographic targeting
• Best Quality Impressions: Tabling events and class visits provide highest-quality direct engagement
• Free Channel Value: COBE internal channels deliver ~45,000 impressions at zero cost
• Newsletter Strategy: Feature certificates every few months with varied messaging to avoid tune-out (per Kate)
• Data Gaps: Yellow-highlighted rows need validation with actual COBE analytics

## Contacts & Process
COBE MARKETING CONTACTS & REQUEST PROCESS
THE GOLDEN RULE: All requests start at cobe-info@boisestate.edu
MARKETING TEAM CONTACTS
Role | Name | Responsibility
Director | Kate Watson | Strategy, approvals, crisis response, newsletter coordination
Mgmt Assistant | Kim Presnell | Social media scheduling, posting logistics
Multimedia | Joe Morgan | Video production, event photography, reels
Graphic Design | McKenna Howard | Visual assets, layout design, Hands-Off creative
Graphic Design | Ann Hottinger | Creative support, template design, Hands-Off creative
REQUEST EMAIL FORMAT
Subject Line: | PROGRAM REQUEST - [Channel] - [Date Range]
Include in Email:
• Channel(s): Instagram, LinkedIn, Email, Web, MBEB screens, Event support
• Target publish/send date(s) and requested cadence
• Campaign objective + success metric (e.g., RSVPs, applications)
• Copy draft (≤100 words) and CTA link (Certificate Landing Page)
• Assets attached with correct sizes and alt text
• Lead owner for approvals
TWO PATHS FOR REQUESTS
HANDS-OFF (Concierge) |  | HANDS-ON (DIY with Support)
You provide: Who, What, When, Where, Photos |  | You create: Copy, Graphics using templates
Marketing handles: Copy, Graphics, Scheduling, Approvals |  | Marketing provides: Templates, Brand Review, Final Approval